## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Mariam | Scott | Grant | Irem | Maryam | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 10 |  | 0.3
|  | Design architecture | Project Manager | Mariam | 10 |  | 0.3 |  | 0.3 | 0 |  |  |  | 0.3
| Requirements |  |  |  |  | 6 |  | 24 | [5 empty] | 0
|  | Gather | Requirements Engineer | Scott, Irem, Grant, Maryam, Mariam | 2 |  | 6 |  | 1 | 0.5 | 0.5 | 1 | 3 | 6
|  | Analyze | Requirements Engineer | Scott, Irem, Grant, Maryam, Mariam | 2 |  | 9 |  | 3 | 1 | 1 | 1 | 3 | 9
|  | Specify | Requirements Engineer | Scott, Irem, Grant, Maryam, Mariam | 2 |  | 9 |  | 2 | 1 | 1 | 2 | 3 | 9
| Documentation |  |  |  |  | 24 |  | 17 | [5 empty] | 0
|  | Project Charter | Project Manager | Mariam | 2 |  | 4 |  | 4 | 0 |  |  |  | 4
|  | Release Plan | Project Manager | Mariam | 2 |  | 0 |  |  | 0 |  |  |  | 0
|  | Requirements Document | Project Manager, Requirements Engineer | Mariam | 3 |  | 5.5 |  | 5 | 0 |  | 0.5 |  | 5.5
|  | Project Plan | Project Manager, Developers | Mariam, Scott, Irem, Grant, Maryam | 5 |  | 3.5 |  | 0 | 2 |  | 1.5 |  | 3.5
|  | Architecture Document | Architect | Scott, Grant, Maryam | 5 |  | 3.5 |  |  | 0.5 |  | 2 | 1 | 3.5
|  | Test Report | Tester | Maryam | 5 |  | 0 |  |  | 0 |  |  |  | 0
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Irem | 2 |  | 0.5 |  |  | 0 |  | 0.5 |  | 0.5
Coding | [6 empty] | 0 | [6 empty] | 0
Iteration 1: | Development |  |  |  |  | 35 |  | 16.55 | [5 empty] | 0
|  | Determine technology needs | Developer | Mariam, Scott, Irem, Grant, Maryam | 1 |  | 1.25 |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 1.25
|  | Research and learn new language and environment(.net framework, react) | Developer | Mariam, Scott, Irem, Grant, Maryam | 20 |  | 13.3 |  | 1 | 3 | 0.3 | 7 | 2
|  | Create a basic .net application | Developer | Scott, Grant, Irem | 2 |  | 1.5 |  |  | 1 |  | 0.5 |  | 1.5
|  | Implement classes | Developer | Scott, Grant, Irem | 10 |  | 0.5 |  |  | 0.5 |  |  |  | 0.5
|  | Unit Testing | Developer | Maryam | 2 |  | 0 |  |  | 0 |  |  |  | 0
| Analysis |  |  |  |  | 6 |  | 3.75 | [5 empty] | 0
|  | System Testing | Tester | Maryam | 2 |  | 0 |  |  | 0 |  |  |  | 0
|  | Bug fix as required | Tester, Developer | Scott, Grant, Irem, Maryam | 2 |  | 0.25 |  |  | 0.25 |  |  |  | 0.25
|  | Evaluate needs for next iteration | Project Manager | Mariam | 2 |  | 3.5 |  | 2 | 0.5 |  |  | 1 | 3.5
Iteration 2: | Design |  |  |  |  | 13 |  | 17 | [5 empty] | 0
|  | Implement any design changes | Project Manager | Mariam | 2 |  | 1 |  | 1 |  |  |  |  | 1
|  | Risk analysis | Project Manager | Mariam | 2 |  | 3 |  | 3 |  |  |  |  | 3
|  | Design HTML format | Developer | Maryam | 2 |  | 3 | [5 empty] | 3 | 3
|  | Design HTML-handling code | Developer | Maryam | 5 |  | 6 | [5 empty] | 6 | 6
|  | Create UI design for balance screen | Developer | Maryam | 2 |  | 4 | [5 empty] | 4 | 4
| Development |  |  |  |  | 22 |  | 21 | [5 empty] | 0
|  | Review requirements | Developer | Maryam, Scott, Irem, Grant | 1 |  | 3 |  |  | 1 | 0.5 | 0.5 | 1 | 3
|  | Create HTML parsing code | Developer | Maryam | 5 |  | 5 | [5 empty] | 5 | 5
|  | Handle HTML data structure for retrieving balance | Developer | Maryam | 10 |  | 5 | [5 empty] | 5 | 5
|  | Implement UI | Developer | Maryam | 4 |  | 5 | [5 empty] | 5 | 5
|  | Unit Testing | Developer | Irem, Grant | 2 |  | 3 |  |  |  | 1 | 2 |  | 3
| Analysis |  |  |  |  | 6 |  | 9.5 | [5 empty] | 0
|  | System Testing | Tester | Irem, Grant | 2 |  | 2 |  |  |  | 1 | 1 |  | 2
|  | Bug fix as required | Tester, Developer | Irem, Grant, Scott, Maryam | 2 |  | 5.5 |  |  | 2 | 0.5 | 2 | 1 | 5.5
|  | Evaluate needs for next iteration | Project Manager | Mariam | 2 |  | 2 |  | 2 |  |  |  |  | 2
Iteration 3: | Design |  |  |  |  | 17 |  | 24 | [5 empty] | 0
|  | Implement any design changes | Project Manager | Mariam | 2 |  | 2 |  | 2 |  |  |  |  | 2
|  | Risk analysis | Project Manager | Mariam | 3 |  | 3 |  | 3 |  |  |  |  | 3
|  | Create UI design for vendor locations | Developer | Scott, Grant, Irem, Maryam | 6 |  | 12 |  |  | 6 | 1 | 3 | 2 | 12
|  | Design data structure for RSS location list | Developer | Scott, Grant, Irem, Maryam | 6 |  | 7 |  |  | 4 | 1 | 1 | 1 | 7
| Development |  |  |  |  | 18 |  | 18.5 | [5 empty] | 0
|  | Review requirements | Developer | Mariam, Irem, Grant, Scott, Maryam | 3 |  | 4.5 |  | 1 | 1 | 0.5 | 1 | 1 | 4.5
|  | Develop code | Developer | Scott | 10 |  | 10 |  |  | 7 |  |  | 3 | 10
|  | Unit Testing | Developer | Irem, Grant | 5 |  | 4 |  |  |  | 2 | 2 |  | 4
| Analysis |  |  |  |  | 9 |  | 11 | [5 empty] | 0
|  | Acceptance Testing | Tester, Project Manager | Irem, Grant, Mariam | 5 |  | 7 |  | 1 | 3 | 3 |  |  | 7
|  | Bug fix as required | Tester, Developer | Irem, Grant, Scott, Maryam | 4 |  | 4 |  |  | 1 | 1 | 1 | 1 | 4
Iteration 4: | Design |  |  |  |  | 4 |  | 5 | [5 empty] | 0
|  | Implement any design changes | Project Manager | Mariam | 1 |  | 2 |  | 2 |  |  |  |  | 2
|  | Design HTML format | Developer | Maryam | 3 |  | 3 | [5 empty] | 3 | 3
| Development |  |  |  |  | 14 |  | 14 | [5 empty] | 0
|  | Fix HTML patterns | Developer | Maryam | 5 |  | 5 | [5 empty] | 5
|  | Develop business logic | Developer | Scott | 5 |  | 5 |  |  | 5 |  |  |  | 5
|  | Unit Testing | Tester, Developer | Irem, Grant | 4 |  | 4 |  |  |  | 2 | 2 |  | 4
| Analysis |  |  |  |  | 10 |  | 10 | [5 empty] | 0
|  | System Testing | Tester | Irem, Grant | 3 |  | 4 |  |  |  | 2 | 2 |  | 4
|  | Bug fix as required | Tester, Developer | Irem, Grant, Scott, Maryam | 5 |  | 5 |  |  | 2 | 1 | 1 | 1 | 5
|  | Evaluate needs for next iteration | Project Manager | Mariam | 2 |  | 1 |  | 1 |  |  |  |  | 1
Iteration 5: | Development |  |  |  |  | 21 | [7 empty] | 0
|  | Fix HTML and CSS patterns as needed | Developer | Scott, Maryam | 7 |  | 0 | [6 empty] | 0
|  | Develop code | Developer | Scott | 5 |  | 0 | [6 empty] | 0
|  | Acceptance Testing | Tester | Irem, Scott | 2
|  | System Testing | Tester | Irem, Grant | 3
|  | Unit Testing | Developer | Irem, Grant | 4 | [8 empty] | 0
| Analysis |  |  |  |  | 4 |  | 0 | [5 empty] | 0
|  | Bug fix as required | Tester, Developer | Irem, Grant, Scott, Maryam | 4 |  | 0 | [6 empty] | 0
Total |  |  |  |  | 219 | 219 | 191.6 | 191.6 | 34.55 | 42.5 | 19.55 | 34.75 | 60.25 | 191.6